## Setup
Sr. no. | Sheet | Detail
1 | Model type 1 | This sheet represents calculation of CoD for the first part of the model.
2 | Model type 2 | This sheet represents calculation of CoD for the second part of the model.
3 | Combination | This sheet shows calculation of CoD for the combination of both parts.
4 | Criteria scoring | This sheet represents each criteria score by using weighted average method.
5 | Matrix | This sheet covers graph and finaly value calculation by using CoD value and crtieria value.
6 | Combine matrix | This sheet represents graph for combine model.
7 | Comparison | This sheet shows prioritiziation of projects based on final value.
Grey area in sheet 2, sheet 3 and sheet 4 show data provided by the company.
Unit | Day Per Unit
Day | 1
Workday | 5
Week | 7
Month | 30
Year | 365
Priority Scale | Value
Low | 1
Medium | 2
Medium/High | 3
High | 4
Critical | 5

## Model type 1
Sr. no. | Model | Activity/Project/Product | Duration | Unit | Budget at completion (BAC) | Planned work completion (%) | Work performed (%) | PV | EV | SV | SPI | Forecasted planned remaining days | Forecasted actual remaining days | Cost/day | Delay days | CoD | Fixed CoD | Total CoD
1 | 1 | Product A | 2 | Month | 6000 | 50 | 40 | 3000 | 2400 | -600 | 0.8 | 30 | 36 | 100 | 6 | 600 | 500 | 1100
2 | 1 | Product B | 3 | Month | 7000 | 30 | 25 | 2100 | 1750 | -350 | 0.83333 | 63 | 67.5 | 77.7778 | 4.5 | 350 | 500 | 850
3 | 1 | Product C | 5 | Month | 12000 | 40 | 30 | 4800 | 3600 | -1200 | 0.75 | 90 | 105 | 80 | 15 | 1200 | 500 | 1700

## Model type 2
Sr. no. | Model | Activity/Project/Product | Budget = EV | AC | CV | CPI | Forecasted sales Volume (V) | Sales price | Unit cost | Margin (M) | Planned profit (P) | SVS | Unit per month | Monthly profit | Peak reduction cost (%) | CV per month | Unit per month due to CV | Unit lost per month | Unit lost per month (%) | Value of x for CoD | CoD | Forecasted profit
1 | 2 | Product A | 6000 | 6500 | -500 | 0.92308 | 50 | 1200 | 1100 | 100 | 5000 | 50 | 4.1667 | 416.6667 | 50% | -41.6667 | 4.1288 | 0.037879 | 0.9091% | 0.50909 | 2545.4545 | 2454.5455
2 | 2 | Product B | 7000 | 8800 | -1800 | 0.79545 | 70 | 2200 | 2100 | 100 | 7000 | 70 | 5.8333 | 583.3333 | 70% | -150 | 5.7619 | 0.071429 | 1.224% | 0.71224 | 4985.7143 | 2014.2857
3 | 2 | Product C | 12000 | 13000 | -1000 | 0.92308 | 60 | 1550 | 1500 | 50 | 3000 | 30 | 5 | 250 | 30% | -83.3333 | 4.9444 | 0.055556 | 1.111% | 0.31111 | 933.3333 | 2066.6667

## Model type 3 (combine)
Sr. no. | Model | Activity/Project/Product | Unit | Duration | Budget | CoD | Fixed CoD | Total CoD of first part | CoD of second part | Total CoD
1 | 3 | Product A | Month | 2 | 6000 | 600 | 500 | 1100 | 2545.45 | 3645.45
2 | 3 | Product B | Month | 3 | 7000 | 350 | 500 | 850 | 4985.71 | 5835.71
3 | 3 | Product C | Month | 5 | 12000 | 1200 | 500 | 1700 | 933.33 | 2633.33

## Criteria scoring
Sr. no. | Model | Activity/Project/Product | Urgency (25%) | Strategic alignment (10%) | Value to customers (10%) | Impact (25%) | Product life cycle (30%) | Criteria Value
1 | 1 | Product A | 4 | 2 | 3 | 4 | 5 | 4
2 | 1 | Product B | 5 | 4 | 4 | 5 | 5 | 4.8
3 | 1 | Product C | 1 | 3 | 2 | 2 | 1 | 1.55
4 | 2 | Product A | 3 | 3 | 4 | 4 | 5 | 3.95
5 | 2 | Product B | 4 | 3 | 4 | 5 | 5 | 4.45
6 | 2 | Product C | 3 | 2 | 1 | 1 | 1 | 1.6
7 | 3 | Product A | 3.5 | 2.5 | 3.5 | 4 | 5 | 3.975
8 | 3 | Product B | 4.5 | 3.5 | 4 | 5 | 5 | 4.625
9 | 3 | Product C | 2 | 2.5 | 1.5 | 1.5 | 1 | 1.575

## Matrix
Sr. no. | Model | Activity/Project/Product | CoD | CoD Scale | Criteria value | Final value
1 | 1 | Product A | 1100 | 2.75 | 4 | 4.8541
2 | 1 | Product B | 850 | 2.125 | 4.05 | 4.5736
3 | 1 | Product C | 1700 | 4.25 | 1.55 | 4.5238
4 | 2 | Product A | 2545.45 | 2.5455 | 3.95 | 4.6991
5 | 2 | Product B | 4985.71 | 4.9857 | 4.45 | 6.6828
6 | 2 | Product C | 933.33 | 0.93333 | 1.6 | 1.8523

## Combine matrix
Sr. no. | Model | Activity/Project/Product | CoD | CoD Scale | Criteria value | Final value
1 | 3 | Product A | 3645.45 | 3.0379 | 3.98 | 5.0069
2 | 3 | Product B | 5835.71 | 4.8631 | 4.63 | 6.7147
3 | 3 | Product C | 2633.33 | 2.1944 | 1.58 | 2.7041

## Comparison
Sr. no. | Model | Activity/Project/Product | CoD | Final value | Priority
1 | 1 | Product A | 1100 | 4.85 | A - B - C
2 | 1 | Product B | 850 | 4.57 | A - B - C
3 | 1 | Product C | 1700 | 4.52 | A - B - C
4 | 2 | Product A | 2545.45 | 4.7 | B - A - C
5 | 2 | Product B | 4985.71 | 6.68 | B - A - C
6 | 2 | Product C | 933.33 | 1.85 | B - A - C
7 | 3 | Product A | 3645.45 | 5.01 | B - A - C
8 | 3 | Product B | 5835.71 | 6.71 | B - A - C
9 | 3 | Product C | 2633.33 | 1.58 | B - A - C